THE IDEA: BÁN ÁO GÂY QUỸ HỘ TRỢ TỪ THIỆN CHO HỘI CỨU TRỢ CHÓ MÈO

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NBs** | **Date** | **Task** | **Executor** | **Detail** |
| 1 | 11/5 to 14/5 | IDEA | All members | Topic, Name of project |
| 2 | 15/5 | Create Website | Trọng Nhân | Post the T-shirt model, where to order and receive orders |
| 3 | 16/5 | Write content | Quang Hưng, Minh Quân | Apply for funds to support the work of buying and designing shirts |
| 4 | 17/5 | Looking for groups that support cats and dogs | Tuấn Trường | Message the admins for support and post moderation for the project |
| 5 | 18/5 | Searching for Shirt Factory | Duy Dương, Tuấn Trường, Minh Quân, Quang Hưng | Check fabric quality in factories |
| 6 | 19/5 | Create Fanpage | Quốc Thắng | Profile photo, cover photo and content for the post |
| 7 | 20/5 | Search Print Studio | Quang Hưng,  Minh Quân | Check print materials and prices |
| 8 | 22/5 đến 25/5 | Proposal writing and print design | All members | Divide each person's writing, prepare for the presentation and finalize the print |
| 9 | 26/5 | Proposal Censorship | All members | Read together, check each other's parts to correct, and review each person's presentation |
| 10 | 27/5 | Closing the sale price | All members | Discuss the total amount of money taken and printed, then calculate the selling price |
| 11 | 28/5 | Browse presentations | All members | Carefully review each presenter so that there are no mistakes |
| **NBs** | **Date** | **Task** | **Executor** | **Detail** |
|  |  |  |  |  |
|  |  |  |  |  |